## Read_Me
VIA monthly project reporting ¦ BLANK INPUT TEMPLATE
Do not publish without source review. This workbook contains no client passwords.
Topic | Instructions
Template version | VIA-REPORT-EXCEL-1.0; one workbook = one project + one reporting month.
Workbook purpose | Filled from the Mughsayl web demo. ALL entered values are DUMMY DATA, not approved project figures.
Current app compatibility | Direct .xlsx import still needs implementation. Do not upload this workbook to the existing CSV-only importer. This workbook defines the proposed Excel import contract.
Start here | Complete Project, Contract_Dates and Progress_Finance. Then complete relevant repeating tables.
Numbers | Enter 95 for 95 percent; percent cells display 95.00%. Enter amounts as numbers, no currency text. Use zero only when explicitly reported.
Missing vs not applicable | Leave missing values blank and select Not reported. Use Not applicable only when the source/team confirms it. Never put NA into a numeric cell.
Dates / identifiers | Use real Excel dates. Report month uses its first day only as a month identifier. Store references and telephone numbers as text to preserve leading zeroes.
Manual assets | Upload logo, project layout and four photographs in the app; record captions and asset IDs on Assets. Additional logos, status drawing and source S-curve image have separate slots. No images need to be embedded in Excel.
Schedule | Copy readable monthly numbers from original Excel/source table. Leave future actuals blank. If unreadable, choose Source image and upload the original S-curve. Never estimate plotted values.
Financial semantics | Financial progress, certified amount, paid amount and anticipated payment are distinct. Never substitute one for another.
Scope and layers | Optional if not reported / not applicable. Never invent five quantities or pavement layers to fill a dashboard.
Editing tables | Keep sheet names, field keys and table headers. Fill existing rows; add rows inside the Excel table if needed. Ignore unused empty rows on import.
Checks | Formula cells are green. Excel recalculates them on opening; they are review aids only. The application must independently validate values on import.
Review | Needs review is NOT verified. Check against the source, mark verified fields, then preview and approve in the app. Workbook approval names do not replace secure app approval.
Example limitations | Example figures are manually transcribed from the supplied image-based PDF and require checking. Tiny S-curve values, unclear contacts and absent data are intentionally left blank.
Sample issue to resolve | Financial difference is printed 4.39%; actual minus planned is -4.39 percentage points. Preserve both and confirm the source convention.
Source coverage | Includes contract/VOs, dates, bridge and arches progress, financial figures, activity table, monthly schedule, resources, scope, narrative updates, contacts, photographs, logos and the separate activity-status drawing.
Demo footer code | DUMMY DATA — NOT FOR REPORTING (current template has no dedicated footer-code field).
Unused entries | Fields not supplied by the demo remain blank, including original contract breakdown and financial planned %.
Project URL | The demo is /demos/mughsayl.html; no live project slug is assigned to this workbook.

## Project
Project
Blue cells: enter data. Keep field keys, headers and sheet names unchanged. Missing numeric data = blank + a status, never invented zero.
Field key | Field label | Value | Unit / type | Requirement | Entry status | Source reference | Instructions / clarification
project_name | Full project name | Construction Works of Mughsayl Road and Bridge | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Copy the approved project title.
project_reference | Project / contract reference | DEMO ONLY / 2026 / 01 | text | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Do not invent an identifier.
project_slug | Existing project URL slug |  | text | Required | Not reported |  | For later months use the SAME project slug. Set once in the app.
project_type | Project type | Illustrative data — not an approved report | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Internal classification; confirm with project team.
region | Region / governorate | Governorate of Dhofar, Sultanate of Oman | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | As printed.
report_month | Reporting month | 2026-07-01 | month | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Enter first day of the report month; displayed as month and year.
report_number | Report number | 17 | text | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Printed page number is NOT the report number.
data_as_of | Exact data-as-of date | 2026-07-31 | date | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Confirm exact date; July 2026 alone does not establish 31 July.
revision | Report revision | Rev-01 | text | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Do not assume Rev-01.
source_filename | Original report filename | http://localhost:8080/demos/mughsayl.html | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Source PDF retained for review.
brief | Project brief | Bridge and approach road works | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Keep full scope and significant qualifications.
prepared_by | Prepared by |  | text | Internal | Not reported |  | Name of person entering this workbook.
checked_by | Checked by |  | text | Internal | Not reported |  | Reviewer name. A workbook name is not an authenticated app approval.
checked_date | Checked date |  | date | Internal | Not reported |  | Actual date reviewed.

## Contract_Dates
Contract Dates
Blue cells: enter data. Keep field keys, headers and sheet names unchanged. Missing numeric data = blank + a status, never invented zero.
Field key | Field label | Value | Unit / type | Requirement | Entry status | Source reference | Instructions / clarification
currency | Currency | R.O. | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Applies to monetary figures.
original_ex_contingency | Original contract excluding contingency |  | amount | Required | Not reported |  | Preserve three decimal places.
contingency | Contingency |  | amount | If reported | Not reported |  | Sample prints Nil; numeric zero is its interpretation, subject to review.
original_inc_contingency | Original contract including contingency |  | amount | Required | Not reported |  | Do not sum variation totals together.
contract_with_vo_1 | Contract with VO.1 and contingency |  | amount | If applicable | Not reported |  | Sample prints NA: keep value blank and select Not applicable.
contract_with_vo_2 | Contract with VO.2 and contingency |  | amount | If applicable | Not reported |  | Sample prints NA: keep value blank and select Not applicable.
contract_with_vo_3 | Contract with VO.3 and contingency |  | amount | If applicable | Not reported |  | Sample prints NA: keep value blank and select Not applicable.
contract_with_vo_4 | Contract with VO.4 and contingency |  | amount | If applicable | Not reported |  | Sample prints NA: keep value blank and select Not applicable.
dashboard_contract_value | Approved contract value used on dashboard | 34844451.558 | amount | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Reviewer selects the applicable current contract basis; do not guess.
contract_basis | Basis of dashboard contract value | Demo dashboard contract value; original/variation breakdown not supplied | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | For example: original including contingency, or approved VO.2 total.
award_date | Awarding date | 2025-01-01 | date | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Enter a real Excel date.
mobilization_days | Mobilization period | 60 | days | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Not automatically added to construction duration.
construction_days | Original construction period | 912 | days | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Sample: 669 days.
start_date | Start of construction | 2025-03-02 | date | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | As printed; reconcile with duration separately.
completion_date | Contract completion date | 2027-08-30 | date | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Original contractual completion date.
construction_days_with_vos | Construction period with VOs |  | days | If applicable | Not reported |  | Sample prints a dash; do not interpret this as zero.
completion_date_with_vos | Completion date with VOs |  | date | If applicable | Not reported |  | Leave blank if unreported.
elapsed_days | Elapsed time | 517 | days | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Reported duration; check against remaining days.
remaining_days | Remaining period | 395 | days | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Do not calculate from today; this is a monthly snapshot.
expected_completion | Expected completion date | 2027-08-30 | date | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Separate from original completion date.

## Progress_Finance
Progress Finance
Blue cells: enter data. Keep field keys, headers and sheet names unchanged. Missing numeric data = blank + a status, never invented zero.
Field key | Field label | Value | Unit / type | Requirement | Entry status | Source reference | Instructions / clarification
physical_planned | Bridge & road cumulative planned progress | 47.95 | percent | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Enter 95 for 95%, NOT 0.95.
physical_actual | Bridge & road cumulative actual progress | 40.94 | percent | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Do not substitute financial progress.
physical_variance_reported | Reported physical ahead / delay | -7.01 | signed percent | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Keep printed sign; calculated actual-minus-planned appears in Checks.
arches_planned | Arches cumulative planned progress |  | percent | If reported | Not reported |  | Arches column is blank in sample. Activity-row figures belong on Activities.
arches_actual | Arches cumulative actual progress |  | percent | If reported | Not reported |  | Do not copy overall bridge progress into this column.
monthly_planned | This-month planned physical progress | 3.72 | percent | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Leave blank if tiny chart table is unreadable.
monthly_actual | This-month actual physical progress | 1.69 | percent | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Never derive by estimating line heights.
financial_planned | Financial cumulative planned progress |  | percent | Required | Not reported |  | Independent of physical planned progress.
financial_actual | Financial cumulative actual progress | 33.38 | percent | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Confirm what this measure represents; do not assume paid / contract.
financial_difference_reported | Printed financial difference |  | signed percent | If reported | Not reported |  | Sample prints +4.39 without a minus; actual-minus-planned is -4.39.
financial_difference_basis | Meaning of reported financial difference |  | text | Needs clarification | Not reported |  | Confirm whether the source uses planned minus actual.
anticipated_payment | Total payment anticipated |  | amount | If reported | Not reported |  | This is NOT total paid or certified amount.
paid_amount | Total actually paid | 10969331.064 | amount | If reported | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Not explicitly provided in sample. Keep blank.
certified_amount | Total certified amount |  | amount | If reported | Not reported |  | Distinct from anticipated and actually paid amounts.
financial_basis | Definition / denominator of financial percentage |  | text | Needs clarification | Not reported |  | Use to determine whether a paid-to-contract comparison is meaningful.
chart_mode | S-curve representation | Verified schedule | text | Required | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Choose Verified schedule or Source image; sample needs original chart/table.
Note on C19: Numerical schedule for demo rendering only. NOT verified project data.

## Activities
Physical progress of major activities
Percentages are percentage points: 100 = 100%. Above 100 is retained for review, not silently capped.
Activity ID | Activity name | Planned % | Actual % | Printed difference % | Calculated actual-plan | Entry status | Source reference | Notes
activity_01 | Mobilization | 60 | 60 | 0 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_02 | Unclassified Excavation | 62.72 | 71.79 | 9.07 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_03 | Unclassified Str. Excavation | 98.97 | 103.4 | 4.43 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_04 | GSB (Class-B) | 43 | 30 | -13 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_05 | ABC (Class-B) | 45.21 | 24.92 | -20.29 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_06 | Bit. Base Course (Class-B) | 43.94 | 19.72 | -24.22 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_07 | Bit. Wearing (Class-B) | 38.1 | 0 | -38.1 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_08 | Concrete C-15 | 78.38 | 78.68 | 0.3 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_09 | Concrete C-35 | 63.67 | 54.82 | -8.85 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_10 | Steel (any dia.) | 65.59 | 52.2 | -13.39 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy activity figures from the demo; not for reporting.
activity_11 | [5 empty] | Not reported
activity_12 | [5 empty] | Not reported
activity_13 | [5 empty] | Not reported
activity_14 | [5 empty] | Not reported
activity_15 | [5 empty] | Not reported
activity_16 | [5 empty] | Not reported
activity_17 | [5 empty] | Not reported
activity_18 | [5 empty] | Not reported
activity_19 | [5 empty] | Not reported
activity_20 | [5 empty] | Not reported
Note on D6: 103.40 is present in the demo and intentionally preserved, not capped at 100.

## Monthly_Schedule
S-curve ¦ monthly source values
Leave month cells blank until original values are available. Chronological order, one row per month; no invented zero start point.
Month | Monthly planned % | Monthly actual % | Cumulative planned % | Cumulative actual % | Monthly actual-plan | Entry status | Source reference | Notes
2025-02-01 | 0.5 | 0.5 | 0.5 | 0.5 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-03-01 | 0.6 | 0.6 | 1.1 | 1.1 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-04-01 | 0.8 | 0.8 | 1.9 | 1.9 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-05-01 | 1.1 | 1.1 | 3 | 3 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-06-01 | 1.5 | 1.5 | 4.5 | 4.5 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-07-01 | 1.8 | 1.8 | 6.3 | 6.3 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-08-01 | 2.1 | 2.1 | 8.4 | 8.4 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-09-01 | 2.5 | 2.5 | 10.9 | 10.9 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-10-01 | 2.8 | 2.8 | 13.7 | 13.7 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-11-01 | 3.1 | 3.1 | 16.8 | 16.8 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2025-12-01 | 3.4 | 3.4 | 20.2 | 20.2 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-01-01 | 3.6 | 3.6 | 23.8 | 23.8 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-02-01 | 3.8 | 3.5 | 27.6 | 27.3 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-03-01 | 3.9 | 3.2 | 31.5 | 30.5 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-04-01 | 4 | 3 | 35.5 | 33.5 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-05-01 | 4.2 | 2.5 | 39.7 | 36 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-06-01 | 4.53 | 3.25 | 44.23 | 39.25 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-07-01 | 3.72 | 1.69 | 47.95 | 40.94 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-08-01 | 4 |  | 51.95 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-09-01 | 4.2 |  | 56.15 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-10-01 | 4.4 |  | 60.55 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-11-01 | 4.6 |  | 65.15 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2026-12-01 | 4.8 |  | 69.95 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-01-01 | 4.5 |  | 74.45 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-02-01 | 4.2 |  | 78.65 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-03-01 | 3.8 |  | 82.45 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-04-01 | 3.5 |  | 85.95 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-05-01 | 3 |  | 88.95 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-06-01 | 2.5 |  | 91.45 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-07-01 | 2 |  | 93.45 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.
2027-08-01 | 6.55 |  | 100 |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy programme; future actuals intentionally blank.

## Resources
Contractor resources
Whole-number counts. Negative variance means actual resources below plan.
Resource | Planned | Actual | Calculated actual-plan | Printed variance | Unit | Entry status | Source reference | Notes
Machinery | 126 | 110 |  | -16 | units | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Manpower | 310 | 290 |  | -20 | persons | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report

## Scope_Layers
Scope quantities and pavement layers
Optional sections: type Scope or Layer. Layer thickness is separate from scope quantity. Blank means not reported.
Type | Stable ID / layer code | Description | Quantity | Unit | Thickness mm | Qualifier / notes | Entry status | Source reference
Scope | scope_01 | Asphalt road length | 28.09 | km |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Scope | scope_02 | Salalah By-pass | 5.521 | km |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Scope | scope_03 | Under-passes | 8 | no. |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Scope | scope_04 | Flyover | 1 | no. |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Scope | scope_05 | Box culverts | 82 | no. |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Layer | BWC | Bituminous Wearing Course |  |  | 50 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Layer | BBC | Bituminous Base Course |  |  | 60 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Layer | ABC | Aggregate Base Course |  |  | 300 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Layer | GSB | Granular Sub-Base |  |  | 200 |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
| item_10 | [5 empty] | Not reported
| item_11 | [5 empty] | Not reported
| item_12 | [5 empty] | Not reported
| item_13 | [5 empty] | Not reported
| item_14 | [5 empty] | Not reported
| item_15 | [5 empty] | Not reported

## Status_Updates
Narrative progress and independent trade status
Preserve the source wording. For example, “in progress (76/76)” needs clarification, not automatic conversion to Complete.
Update ID | Description / source wording | Explicit trade status | Entry status | Source reference | Clarification / internal note
update_01 | Protection — cut slope | Active | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_02 | Utilities | Active | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_03 | Land acquisition | Complete | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_04 | Culverts / retaining walls | Complete | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_05 | Bridges / tunnels | Active | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_06 | Pedestrian over/underpass | Active | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_07 | Earthworks | Complete | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_08 | Subbase layer | Behind | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_09 | Aggregate base course | Behind | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_10 | Bit. base course | Behind | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_11 | Bit. wearing course | Not started | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_12 | Protection — embankment | Active | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report | Dummy trade status
update_13 |  | Unknown | Not reported
update_14 |  | Unknown | Not reported
update_15 |  | Unknown | Not reported
update_16 |  | Unknown | Not reported
update_17 |  | Unknown | Not reported
update_18 |  | Unknown | Not reported
update_19 |  | Unknown | Not reported
update_20 |  | Unknown | Not reported

## Contacts
Project parties and contacts
Enter telephone numbers as TEXT. Unclear small-print names and numbers were not guessed in the example.
Party role | Organisation | Department | Representative | Position / title | Telephone | Email | Entry status | Source reference
Client | Example Transport Authority | Roads & Land Transport |  |  |  |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Consultant | VIA International — Engineering Consultancy |  | Demo Resident Engineer | Resident Engineer | Demo contact |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Contractor | Example Road & Bridge Contractor |  | Demo Project Manager | Project Manager | Demo contact |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Client representative |  |  | Demo Client Representative |  | Demo contact |  | Needs review | Mughsayl HTML demo — DUMMY DATA, not an approved report
Other contact | [6 empty] | Not reported

## Assets
Manual image uploads and captions
Upload files separately in the app. Match using Asset ID, not filename guesses. Images are not embedded in this workbook.
Asset ID | Purpose | Requirement | Local filename | Caption | Secondary description | Capture date | Entry status | Upload guidance
logo_main | Main dashboard logo | Required | Dashboard/via/logo-color.png |  |  |  | Needs review | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
layout_main | Location / project layout | Required | Dashboard/Raysut dashboard.html | Raysut reference illustration — demo only |  |  | Needs review | Embedded vector schematic, not an uploaded image. Requires the Raysut reference-layout option; not transferable to another route.
photo_1 | Construction photo 1 | Required | Dashboard/Photo1.jpg | Pier foundation backfill | Reference photograph — demonstration only |  | Needs review | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
photo_2 | Construction photo 2 | Required | Dashboard/Photo2.jpg | Bitumen base course layer | Reference photograph — demonstration only |  | Needs review | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
photo_3 | Construction photo 3 | Required | Dashboard/Photo3.jpg | Utilities future ducts | Reference photograph — demonstration only |  | Needs review | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
photo_4 | Construction photo 4 | Required | Dashboard/Photo4.jpg | I-girder work in progress | Reference photograph — demonstration only |  | Needs review | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
logo_client | Additional client logo | Optional |  |  |  |  | Not reported | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
logo_contractor | Additional contractor logo | Optional |  |  |  |  | Not reported | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
status_drawing | Activity-status drawing | If reported |  |  |  |  | Not reported | JPG/PNG/WebP. Keep original resolution; do not upscale to imply extra detail.
s_curve | Original S-curve image | If chart table unreadable |  |  |  |  | Not reported | Interactive chart is populated from Monthly_Schedule, not a picture.

## Checks
Review checklist and calculated comparisons
Checks are not a certification of accuracy. Formula results calculate when opened in Excel.
Check | Result | Reviewer guidance
Physical actual minus planned |  | Percentage points; compare with the printed physical variance.
Financial actual minus planned |  | Sample result -4.39; source prints +4.39. Confirm convention.
Elapsed + remaining - construction |  | Zero means reported durations reconcile. Sample: 636 + 33 = 669.
Original including contingency minus components |  | Zero means monetary components reconcile.
Days between original start and completion |  | Calendar subtraction, excluding the starting day. Compare with contractual counting rules, not an automatic error.
Source schedule readability | MANUAL CHECK | Tiny chart table in sample was not transcribed. Supply original data or source image.
Project identity and reporting month | MANUAL CHECK | Confirm uploaded PDF, workbook and selected existing project all match.
Images and captions | MANUAL CHECK | Check main logo, layout, all four photos and any supplemental drawings.
Publication approval | NOT APPROVED — DUMMY DATA | Preview and approve inside the app after resolving all required fields and review issues.