## Project report
section | field | value | planned | actual | instructions
__section__ | PROJECT REPORT — complete the sections below
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused.
__section__ | 01. PROJECT SETUP — fill once, update only when details change
__section__ | Used in the dashboard heading, timeline, resources and project parties; applicable details also appear in the PDF.
__section__ | Enter project details and approved dates. Contact numbers are text. Use the same project URL for monthly updates. Upload the project layout image in the app; it is shared by the PDF and dashboard.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Project detail | Enter value | Not used | Not used | What to enter
__section__ | PROJECT IDENTITY — name, location, client and description
project | Project URL slug | sample-mughsayl-road-and-bridge |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Existing project URL; required when reusing a saved layout
project | Project number | DEMO ONLY / 2026 / 01 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Project or contract reference
project | Project type | Illustrative data — not an approved report |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Dashboard project classification
project | Project name | SAMPLE — Mughsayl Road and Bridge |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Full project title
project | Region | Governorate of Dhofar, Sultanate of Oman |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Governorate or location
project | Client | Example Transport Authority |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Client or ministry name
project | Client department | Roads & Land Transport |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Department name
project | Brief description | Bridge and approach road works |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Scope and description; Excel will quote commas and line breaks
__section__ | CONTRACT & TIMELINE — approved amount, dates and durations
project | Approved contract total | 34844451.558 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Number without currency; keep all decimals
project | Currency | R.O. |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. R.O. or OMR for this PDF design
project | Award date | 2025-01-01 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD
project | Start date | 2025-03-02 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD
project | Completion date | 2027-08-30 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD
project | Mobilization days | 60 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Whole days
project | Construction days | 912 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Whole days
project | Construction days with VOs |  |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. As agreed including variations; leave blank if unknown
project | Completion date with VOs |  |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD; leave blank if unknown
__section__ | PLANNED RESOURCES — approved people and equipment targets
project | Planned manpower | 310 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Number of people
project | Planned machinery | 126 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Number of machines
__section__ | PROJECT PARTIES — organisations and contact people
project | Consultant | VIA International — Engineering Consultancy |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Organisation name
project | Consultant representative | Demo Resident Engineer |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Name
project | Consultant role | Resident Engineer |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Job title
project | Consultant phone | 00000000 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Set Excel cell format to Text to preserve leading zeros
project | Contractor | Example Road & Bridge Contractor |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Organisation name
project | Contractor representative | Demo Project Manager |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Name
project | Contractor role | Project Manager |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Job title
project | Contractor phone | 00000000 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Set Excel cell format to Text to preserve leading zeros
project | Client engineer | Demo Client Representative |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Name
project | Client engineer phone | 00000000 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Set Excel cell format to Text to preserve leading zeros
__section__ | 02. MONTHLY REPORT — update for each reporting period
__section__ | Feeds the five dashboard summary cards, reporting date, timeline and PDF progress tables.
__section__ | Enter cumulative progress separately from this month's progress. Use 47.95 for 47.95%. Paid amount is money actually paid, not anticipated payment.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Monthly figure | Enter value | Not used | Not used | What to enter
__section__ | REPORT PERIOD & TIME — report reference, date and elapsed days
monthly | Report number | 17 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Monthly report number
monthly | Footer code | DUMMY DATA — NOT FOR REPORTING |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Dashboard footer reference
monthly | Data as of | 2026-07-31 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD; report month is calculated from this date
monthly | Revision | Rev-01 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. For example Rev-01
monthly | Elapsed days | 517 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Whole days; remaining days are calculated if left blank
monthly | Remaining days | 395 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Optional override of construction days minus elapsed days
monthly | Expected completion date | 2027-08-30 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. YYYY-MM-DD; leave blank if unknown
monthly | This month planned % | 3.72 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. This month only; no percent sign
monthly | This month actual % | 1.69 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. This month only; no percent sign
__section__ | PHYSICAL PROGRESS — cumulative and this month
monthly | Cumulative planned progress % | 47.95 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Enter 47.95 for 47.95 percent
monthly | Cumulative actual progress % | 40.94 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Enter 40.94 for 40.94 percent
__section__ | FINANCIAL PROGRESS — percentage and actual payments
monthly | Planned financial progress % | 36.50 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Percentage; preserve source precision
monthly | Actual financial progress % | 33.38 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Percentage; not calculated from paid amount
monthly | Actually paid amount | 10969331.064 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Paid amount in the project currency; not anticipated payment
__section__ | ACTUAL RESOURCES — people and equipment this month
monthly | Actual manpower | 290 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Number of people this month
monthly | Actual machinery | 110 |  |  | DUMMY DEMO DATA — NOT FOR REPORTING. Number of machines this month
__section__ | 03. CONTRACT BREAKDOWN — approved contract amounts
__section__ | Fills the PDF contract-value table. The dashboard's contract total is selected separately in Project setup.
__section__ | Enter each approved total, not the amount to add to another row. Use Nil or NA only when confirmed; leave unknown values blank.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Contract item | Amount / Nil / NA | Not used | Not used | What to enter
contract | Original contract (No Cont.) | 34844451.558 |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Contingency | 0 |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Original contract (with Cont.) | 34844451.558 |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Contract (with VO.1) | NA |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Contract (with VO.2) | NA |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Contract (with VO.3 & Cont.) | NA |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
contract | Contract (with VO.4 & Cont.) | NA |  |  | SAMPLE ONLY — replace with approved project values. Original contract excludes/includes contingency as labelled; variation totals are NA in this example.
__section__ | 04. MAJOR ACTIVITIES — planned versus actual work
__section__ | Creates the dashboard activity bars and PDF physical-progress table. Differences are calculated automatically.
__section__ | One activity per row. Enter cumulative percentages for the reporting date. Leave unused rows blank; maximum 13 for the PDF.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Activity name | Leave blank | Planned % | Actual % | What to enter
activity | Mobilization |  | 60 | 60 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Unclassified Excavation |  | 62.72 | 71.79 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Unclassified Str. Excavation |  | 98.97 | 103.4 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | GSB (Class-B) |  | 43 | 30 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | ABC (Class-B) |  | 45.21 | 24.92 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Bit. Base Course (Class-B) |  | 43.94 | 19.72 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Bit. Wearing (Class-B) |  | 38.1 | 0 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Concrete C-15 |  | 78.38 | 78.68 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Concrete C-35 |  | 63.67 | 54.82 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity | Steel (any dia.) |  | 65.59 | 52.2 | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity |  |  |  |  | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity |  |  |  |  | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
activity |  |  |  |  | Activity name in B; cumulative planned percentage in D and cumulative actual percentage in E. C stays blank. The app calculates actual minus planned.
__section__ | 05. S-CURVE — complete monthly programme
__section__ | Generates the interactive dashboard graph and the PDF graph automatically. Cumulative totals are calculated from these monthly figures.
__section__ | Start at the first programme month and include every month to completion. Enter each month's increment, NOT cumulative totals. Leave future actuals blank; use 0 for a verified month with no progress.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Month (e.g. Jul-26) | Leave blank | Monthly planned % | Monthly actual % | What to enter
schedule | Feb-25 |  | 0.5 | 0.5 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Mar-25 |  | 0.6 | 0.6 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Apr-25 |  | 0.8 | 0.8 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | May-25 |  | 1.1 | 1.1 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jun-25 |  | 1.5 | 1.5 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jul-25 |  | 1.8 | 1.8 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Aug-25 |  | 2.1 | 2.1 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Sep-25 |  | 2.5 | 2.5 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Oct-25 |  | 2.8 | 2.8 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Nov-25 |  | 3.1 | 3.1 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Dec-25 |  | 3.4 | 3.4 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jan-26 |  | 3.6 | 3.6 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Feb-26 |  | 3.8 | 3.5 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Mar-26 |  | 3.9 | 3.2 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Apr-26 |  | 4 | 3 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | May-26 |  | 4.2 | 2.5 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jun-26 |  | 4.53 | 3.25 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jul-26 |  | 3.72 | 1.69 | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Aug-26 |  | 4 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Sep-26 |  | 4.2 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Oct-26 |  | 4.4 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Nov-26 |  | 4.6 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Dec-26 |  | 4.8 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jan-27 |  | 4.5 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Feb-27 |  | 4.2 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Mar-27 |  | 3.8 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Apr-27 |  | 3.5 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | May-27 |  | 3 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jun-27 |  | 2.5 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Jul-27 |  | 2 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule | Aug-27 |  | 6.55 |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule |  |  |  |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule |  |  |  |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule |  |  |  |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule |  |  |  |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
schedule |  |  |  |  | Month in B; monthly planned increment in D; monthly actual increment in E. C stays blank. Future actuals remain blank.
__section__ | 06. PROJECT SCOPE — what is being built
__section__ | Fills the dashboard Scope & build-up quantities. These are quantities, not progress percentages.
__section__ | Up to five items. Enter a description, quantity and unit: for example Bridge length ¦ 540 ¦ m. Only include items relevant to this project.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Scope description | Quantity | Unit (km / m / no.) | Leave blank | What to enter
scope | Asphalt road length | 28.09 | km |  | Describe the item in column B; enter its quantity in C and unit in D. Column E stays blank.
scope | Salalah By-pass | 5.521 | km |  | Describe the item in column B; enter its quantity in C and unit in D. Column E stays blank.
scope | Under-passes | 8 | no. |  | Describe the item in column B; enter its quantity in C and unit in D. Column E stays blank.
scope | Flyover | 1 | no. |  | Describe the item in column B; enter its quantity in C and unit in D. Column E stays blank.
scope | Box culverts | 82 | no. |  | Describe the item in column B; enter its quantity in C and unit in D. Column E stays blank.
__section__ | 07. PAVEMENT LAYERS — road construction build-up
__section__ | Fills the dashboard pavement stack. Layer thickness is measured in millimetres.
__section__ | List layers from top surface downwards. Example: BWC ¦ Wearing course ¦ 50. Leave unused rows blank.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Layer code | Layer description | Thickness (mm) | Leave blank | What to enter
layer | BWC | Bituminous Wearing Course | 50 |  | Enter the code in B, description in C and thickness in millimetres in D. Column E stays blank.
layer | BBC | Bituminous Base Course | 60 |  | Enter the code in B, description in C and thickness in millimetres in D. Column E stays blank.
layer | ABC | Aggregate Base Course | 300 |  | Enter the code in B, description in C and thickness in millimetres in D. Column E stays blank.
layer | GSB | Granular Sub-Base | 200 |  | Enter the code in B, description in C and thickness in millimetres in D. Column E stays blank.
__section__ | 08. TRADE STATUS — current state of each work category
__section__ | Controls the coloured status dots in the dashboard. This does not set route-section colours or create the PDF activity-status drawing.
__section__ | Use complete, active, behind, notstarted or unknown. Use a short trade name, not a long progress narrative. Up to 12 trades.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Trade name | Status | Leave blank | Leave blank | What to enter
trade | Protection — cut slope | active |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Utilities | active |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Land acquisition | complete |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Culverts / retaining walls | complete |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Bridges / tunnels | active |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Pedestrian over/underpass | active |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Earthworks | complete |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Subbase layer | behind |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Aggregate base course | behind |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Bit. base course | behind |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Bit. wearing course | notstarted |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
trade | Protection — embankment | active |  |  | Short trade name in B. Choose its status in C. D and E stay blank.
__section__ | 09. CONSTRUCTION PHOTOS — captions only
__section__ | Captions appear below the four photographs in the PDF and dashboard. Upload the image files in the app.
__section__ | Photo 1: top-left; 2: top-right; 3: bottom-left; 4: bottom-right. Keep the photo IDs unchanged. Logos are uploaded separately.
__section__ | DUMMY DEMO DATA — not for reporting. Blue cells are inputs; grey cells are labels or unused. Blank means unknown, not zero.
__section__ | Photo position ID | Caption | Not used | Not used | What to enter
photo | photo_1 | Pier foundation backfill |  |  | Keep the photo ID in B and enter its caption in C. Upload the matching photograph separately in the app. Order: photo_1 top-left, photo_2 top-right, photo_3 bottom-left, photo_4 bottom-right.
photo | photo_2 | Bitumen base course layer |  |  | Keep the photo ID in B and enter its caption in C. Upload the matching photograph separately in the app. Order: photo_1 top-left, photo_2 top-right, photo_3 bottom-left, photo_4 bottom-right.
photo | photo_3 | Utilities future ducts |  |  | Keep the photo ID in B and enter its caption in C. Upload the matching photograph separately in the app. Order: photo_1 top-left, photo_2 top-right, photo_3 bottom-left, photo_4 bottom-right.
photo | photo_4 | I-girder work in progress |  |  | Keep the photo ID in B and enter its caption in C. Upload the matching photograph separately in the app. Order: photo_1 top-left, photo_2 top-right, photo_3 bottom-left, photo_4 bottom-right.